## Sheet1
		October		November				December					January				February				March					April				May				June
Tasks	w/c	21	28	4	11	18	25	2	9	16	23	30	6	13	20	27	3	10	17	24	2	9	16	23	30	6	13	20	27	4	11	18	25	1	8
Preliminary Work											Xmas				Exams
Familiarise with LiveScan3D
Research Implementation
Server OpenGL Display Developments
Implement Transformer
Implement DisplayFrameTransformer
Mobile AR Development
Setup mobile AR development
Add server-UE network IDs
Multi-source mobile AR
iOS mobile AR migration
Local frame UE delivery
Additional Server Developments
Server UI updates
Multi-source settings
Added SourceCollection with stale source cleaner
Client-Server Multi-source
Merge Selinis’ non-blocking work
Client-server source IDs
Frame Rate Throttling
Integrate Selinis’ dyanmic step work
Completing dynamic step implementation
Write-up
Mid-year report
Dissertation writing
Frame-rate throttling data collection
Prepare Viva

COVID-19 Quarantine =